## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1
3651517 | 68457 | ATM Project | 16 | ATM_1-16 | 293181 | Bug |  |  | 63980 | 1.1 | MFT: Test Case 7 - The program crashes when PIN value is very big | Defect still exists in version 1.1 The function being tested: Authentication The initial state of the system: The system is asking for entry of the PIN Steps to reproduce the defect/bug: Insert a card, then enter the correct card number and the largest possible PIN What was the expected outcome? The system displays a menu of transaction types What was the actual outcome? Program crashed | 2 | In Progress | 3 | Normal | [6 empty] | 320080 | LAB1-Group32 | Jan. 26, 2022 13:38 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:48 | 0 | 0
3650869 | 68457 | ATM Project | 15 | ATM_1-15 | 293181 | Bug |  |  | 63980 | 1.1 | MFT: Test Case 22, system gives incorrect balance after customer inserts an envelope when depositing. | i. Function being tested: System performs a legitimate transaction properly. ii. System is requesting the customer to insert an envelope. iii. Insert an envelope. iv. System accepts envelope. Prints a correct receipt showing amount and correct updated balance. System records transaction correctly in the log (showing message to the bank, approval back, and acceptance of the envelope. v. Systems accepts the envelope, prints the correct log, and prints a receipt in the correct format. However, the balance in the receipt is incorrect. It showed a balance increase of only $10 when $20 was deposited. | 3 | Resolved | 3 | Normal | [6 empty] | 320080 | LAB1-Group32 | Jan. 26, 2022 06:26 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:14 | 0 | 0
3649823 | 68457 | ATM Project | 14 | ATM_1-14 | 293181 | Bug | 92651 | Withdraw Session | 63980 | 1.1 | MFT [16] Withdraw account limit not working | The function being tested: System verifies that customer's balance is sufficient to fulfill the request The initial state of the system: System is requesting a withdrawal amount Steps to reproduce the defect/bug: Insert a valid card and pin, click withdraw then checking then choose an amount that the system currently has but which is greater than the account balance. In this case card 1, pin 42, and choose option 5)$200 which is greater than $100 (available balance) What was the expected outcome? System displays an appropriate message and offers customer the option of choosing to do another transaction or not. What was the actual outcome? System outputs $20 and creates a receit with that amount | 3 | Resolved | 2 | High | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 22:49 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:31 | 0 | 0
3649812 | 68457 | ATM Project | 13 | ATM_1-13 | 293181 | Bug | 92651 | Withdraw Session | 63980 | 1.1 | MFT [14] Withdrawal amount wrong | The function being tested: System performs a legitimate withdrawal transaction properly The initial state of the system: System is displaying the menu of withdrawal amounts Steps to reproduce the defect/bug : enter valid card and pin, selected withdraw then checking then choose an amount that the system currently has and which is not greater than the account balance. This specific case card 1 was chosen with 42 as pin, and with $100 available I selected option 3)$60 to withdraw What was the expected outcome?$60 being withdrawed and proper receit be made What was the actual outcome? $100 was withdrawed and receit was made stating the $100 value | 3 | Resolved | 2 | High | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 22:37 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:31 | 0 | 0
3648606 | 68457 | ATM Project | 12 | ATM_1-12 | 293181 | Bug |  |  | 63980 | 1.1 | MFT 34: Log and Receipt show different card numbers | “MFT:“ (Manual Functional Testing) - Test Case 34 , Defect Still Exists in Version 1.1 i. System performs a legitimate inquiry transaction properly ii. System is displaying menu of account types iii. Choose checking account iv. System prints a correct receipt showing correct balance; System records transaction correctly in the log (showing both message to the bank and approval back) v. The correct balance is shown, but the card numbers in the log compared to the receipt are incorrect. Log shows card 1 while receipt shown. | 2 | In Progress | 3 | Normal | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 17:04 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:27 | 0 | 0
3648604 | 68457 | ATM Project | 11 | ATM_1-11 | 293181 | Bug |  |  | 63980 | 1.1 | MFT 33: Wrong account types in balance inquiry | “MFT:“ (Manual Functional Testing) - Test Case 33 i. System asks customer to choose an account to inquire about ii. Menu of transaction types is being displayed iii. Choose Inquiry transaction iv. System displays a menu of account types v. System displays the wrong types of accounts for card number 1. System shows checking account and money market account when card 1 only has checking and savings accounts. | 3 | Resolved | 3 | Normal | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 16:56 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:22 | 0 | 0 | Jan. 26, 2022 16:22 LAB1-Group32 ATM now shows the correct accounts and does not open invalid accounts
3648597 | 68457 | ATM Project | 10 | ATM_1-10 | 293184 | Other |  |  | 63980 | 1.1 | Bad English | Steps to reproduce the defect/bug: Go and deposit some amount of money. You will be asked if you want to deposit more money with bad English. What was expected to be written? Would. What was written? Wood. | 3 | Resolved | 3 | Normal | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 16:39 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:22 | 0 | 0
3648595 | 68457 | ATM Project | 9 | ATM_1-9 | 293181 | Bug |  |  | 63980 | 1.1 | Balance Inquiry for Money Market account prints Error | i. Balance Inquiry for Money Market account. ii. System is on and idle. User is selecting options for ATM usage. iii. On account card 1, choose "4. Balance Inquiry" then "2. Money Market" iv. Nothing printed because account 1 doesn't have a monkey market account v. "Unknown Error" is shown on ATM window and the balance for the savings account is printed on receipt | 3 | Resolved | 3 | Normal | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 16:35 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:18 | 0 | 0
3648594 | 68457 | ATM Project | 8 | ATM_1-8 | 293181 | Bug | 92653 | Transfer | 63980 | 1.1 | Unable to transfer | The function being tested: Transfer The initial state of the system: System is on and waiting for output Steps to reproduce the defect/bug: Insert card number 2, a valid PIN, select Transfer, then transfer between accounts is not working. What was the expected outcome? A successful transfer is made. What was the actual outcome? Invalid to account type error. | 3 | Resolved | 2 | High | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 16:32 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:28 | 0 | 0
3648593 | 68457 | ATM Project | 7 | ATM_1-7 | 293182 | Task |  |  | 63980 | 1.1 | ATM reduces user's balance when inputting 0 as a deposit. | i. Function being tested is the deposit function. ii. The initial state of the system is waiting for the user to deposit an amount of money in any of their accounts. (After the user has inputted a correct card and PIN and is in the deposit screen). iii. To reproduce this bug, log on with a valid card number, such as 1, put the correct pin, 42 in the case of 1. Check balance inquiry first, it should be equal to $100. Then go to the deposit screen. Click on 0, then press enter. iv. Expected outcome should still be $100 dollars, as the user did not withdraw any money. v. Actual outcome is $90.00, subtracting $10 from the user. | 3 | Resolved | 3 | Normal | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 16:32 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:20 | 0 | 0 | Jan. 26, 2022 16:20 LAB1-Group32 ATM now charges the correct amount of $0.10 for the deposit fee
3648591 | 68457 | ATM Project | 6 | ATM_1-6 | 293182 | Task |  |  | 63980 | 1.1 | Correct PIN does not work after entering an incorrect pin. | i. Function being tested in the entering PIN function. ii. The state of the system: Card is in, waiting for user to input a PIN. iii. To reproduce the bug, enter a correct card number, such as 1. Then input a wrong PIN, such as 541. Then try putting the correct PIN, which is 42. iv. Expected Outcome: Systems accepts customer's card and shows possible transactions the user can take. v. Actual Outcome: PIN is not correctly read, ATM asks user to input a PIN again. | 2 | In Progress | 3 | Normal | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 16:25 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:17 | 0 | 0 | Jan. 26, 2022 16:17 LAB1-Group32 Defect still exists in version 1.1
3648589 | 68457 | ATM Project | 5 | ATM_1-5 | 293181 | Bug | 92652 | Deposit Session | 63980 | 1.1 | Big value input made program crash - Deposit | Defect still exists in version 1.1 The function being tested: PIN input The initial state of the system: The system is on and waiting for input Steps to reproduce the defect/bug: Insert card number 1, a valid PIN, select Deposit, then check and then input the largest possible value. What was the expected outcome? Failure to deposit. What was the actual outcome? Program crashed. | 2 | In Progress | 2 | High | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 16:24 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:34 | 0 | 0
3648587 | 68457 | ATM Project | 4 | ATM_1-4 | 293182 | Task |  |  | 63980 | 1.1 | System crashes (ATM does not respond) when entering a PIN for invalid card number 3 only. | i. Function being tested is the PIN entry function. ii. State of the system is waiting for a user to enter their PIN. However, this is after inputting the number 3 as a card number, which should be an invalid card number to begin with. iii. Turn the ATM on, add a valid number of 20 dollar bills, input "3" as the card number. And input any PIN number. System will crash and not respond anymore. iv. Expected outcome: "Failure, invalid card" and card is ejected. v. Actual outcome: System freezes/crashes. Does not respond to anymore input. | 3 | Resolved | 3 | Normal | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 16:21 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:16 | 0 | 0
3648586 | 68457 | ATM Project | 3 | ATM_1-3 | 293181 | Bug | 92651 | Withdraw Session | 63980 | 1.1 | Invalid Withdraw | Defect still exists in version 1.1 The function being tested: Withdraw The initial state of the system: The system is on and waiting for input Steps to reproduce the defect/bug: Enter a valid card with a valid PIN and click to withdraw and select check-in. Then click a number that is not one of the options. What was the expected outcome? Nothing to happen or an error message. What was the actual outcome? $20 dollars coming out. | 2 | In Progress | 2 | High | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 16:20 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:35 | 0 | 0
3648581 | 68457 | ATM Project | 2 | ATM_1-2 | 293181 | Bug | 92650 | Authentication | 63980 | 1.1 | Big PIN made program crash - Login | Defect still exists in version 1.1 The function being tested: PIN input The initial state of the system: System is on and waiting for input Steps to reproduce the defect/bug: Insert card number 1 and the largest possible PIN What was the expected outcome? Failure to login. What was the actual outcome? Program crashed. | 2 | In Progress | 2 | High | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 16:16 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:37 | 0 | 0
3648579 | 68457 | ATM Project | 1 | ATM_1-1 | 293181 | Bug |  |  | 63980 | 1.1 | Incorrect Card Number Being Read | i. Testing the login function. (Entering the card number) ii. System is on and idle, ATM is at the step after the number of bills was verified, waiting for a correct user. iii. Turned ATM on using the "on" button, input a number of $20 bills. Enter a positive integer as the card number that is not 1 or 2. . iv. Expected outcome should eject the card. "Card cannot be read". v. Actual outcome, ATM accepts the card and takes you to the enter pin screen. | 3 | Resolved | 3 | Normal | [6 empty] | 320080 | LAB1-Group32 | Jan. 25, 2022 16:15 |  | 320080 | LAB1-Group32 | Jan. 26, 2022 16:14 | 0 | 0 | Jan. 26, 2022 16:14 LAB1-Group32 Closed - intended functionality